## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
E01a | create account | As a Bank Employee, I want to know a customer's name, address and date of birth and the type of account Once getting this personal information, I can enter the details to the system So that I can add new customer to the system and give this person a unique account number and pin. | 1 | 1 | •Make sure that the system would add the new customer and his/her account to the bank system and store the customer's information. |  | 25nd March | 7th April
E01b | confirm credit status | As a Bank Employee, I want to know customer status to check whether this person could open account | 1 | 1 | •Verify that customer exists in system matching details given. |  | 27nd March | 8th April
E02a | deposit cash | As a depositor, I want to supply the account number and pin and the amount of cash to be deposited so that I can store money to the account. | 1 | 2 | ·Make sure that the account exists matching account number and account PIN. ·Make sure that the account is not suspended, otherwise customer could not do anything. ·Make sure that deposit is marked as cleared. |  | 7th April | 23th April
E02b | deposit cheque | As a depositor, I want to supply the account number and the amount of cheque to be deposited so that I can deposit funds to the account. | 1 | 2 | ·Make sure that the account exists matching account number and account PIN. ·Make sure that the account is not suspended, otherwise the cash can not be deposited. ·Make sure that an receipt is issued to depositor. ·Make sure that deposit is marked as uncleared |  | 7th April | 20th April
E03 | clear funds | As a customer, I want to clear un-cleared funds. | 5 | 4 | ·Make sure that the unclear money of each account is set to 0.0. |  | 7th May | 20th May
E04 | withdraw funds | As a customer, I want to supply my account number, the correct PIN, and the amount to be withdrawn so that I can withdraw money from my accouont. | 1 | 2 | ·Make sure that the account exists matching account number and account PIN. ·Make sure that the account is not suspended, otherwise person could not do any operation . ·Make sure that the balance is updated. |  | 7th April | 20th April
E05a | suspend account | As a Bank Employee, I want to suspended an account so that no further transaction may occur until the account is recovered. | 4 | 3 | ·Make sure that the account exists matching account number and account PIN. ·Make sure that the information is updated. |  | 22nd April | 5th May
E05b | recover account | As a Bank Employee, I want to recover the suspended account so that the account could make transaction in active state. | 4 | 3 | ·Make sure that the account exists matching account number and account PIN. ·Make sure that the information is updated. |  | 22nd April | 5th May
E06 | close account | As a Bank Employee, I want to check if the account balance and unclear money are both zero so that I can close the account. | 3 | 3 | ·Make sure that the account exists matching account number and account PIN. ·Make sure that a message is issued to customer. ·Make sure that the account balance and unclear money are both zero. |  | 22nd April | 5th May
E07 | save account | As a Bank Employee, I want to store all the accounts so that the information of all accounts can be recorded for further trasaction. | 4 | 4 | ·Make sure that all the accounts would be stored in different text file. |  | 7th May | 9th May